## Introduction and instruction
OSM READINESS TOOL
ASSESSING OSM CAPABILITY and CAPACITY (V1.0)
The OSM Readiness Tool (V1.0) was developed in response to a request by industry partners, SBEnrc Project 2.2 Offsite Fabrication. The problem identified was: "What will enable us to determine if Off-Ssite Manufacture (OSM) is suitable for a building project?" International studies indicate that benefits are accrued if OSM is considered at early stages and incorporated into the design. Successful OSM adoption can be increased though planning and engagement with all OSM stakeholders throughout the entire building process. Having OSM capability and capacity information available will assist the project team with decision-making concering adopting an OSM procurement model. Timing of the decision to adopt an OSM procurement model effects project outcomes. • Early adoption of the OSM procurement model, with input from a wide variety of OSM stakeholders, is considered the low risk option. A high level of stakeholder engagement provides information concerning the availability of essential OSM capability and capacity. Expertise, from a wide range of stakeholders, supports integration of OSM into the total project at the Arrange Team stage. • Adopting OSM at the Tendering stage could mean additional delays for delivery and possible problems with integrating OSM specifications into the Shop Drawings. Adopting an OSM procurement strategy after the Detail Design is completed can benefit a building project, but the benefits afforded by early AEC knowledge sharing relationships will be limited, thus constraining the effectiveness of an OSM procurement model indicating a medium level of risk. • Adopting OSM at the Construction stage of a project is always an option. But, the lack of early project team planning and engagement will certainly mean delays and difficulty with on-site installation. Thus, late adoption of an OSM procurement model is considered a high risk delivery strategy.
Key OSM Issues
1 Risk
2 Knowledge Management
3 Design
4 Procurement
Three-Step OSM READINESS TOOL
The OSM Readiness Tool (V1.0) provides a method for evaluating the capacity and readiness of the project stakeholders, in order to facilitate OSM procurement. There are three steps to the OSM Readiness Tool (V1.0): understanding the project environment, recording knowledge, experience and capacity which enables the evaluation of OSM capability. The aim of the three steps is to inform the decision to use OSM as a building project procurement methodology.
Step 1: Consider the 19 essential questions (available at SBEnrc.com.au, Project 2.2 in the OSM Readiness Tool (V1.0) pdf); Step 2: collect OSM capability and capacity information in OSM_ KnowledgeBank (V1.0) templates; Step 3: evaluate and score OSM capability and capacity.
OSM_KnowledgeBank Instructions
Step 2: collect OSM capability and capacity information using the OSM_KnowledgeBank (V.1.0) templates
Development of an OSM_KnowledgeBank is the responsibility of the client and project manager and is most effective if completed during the ‘Arrange Project Team’ phase of a project. The templates for 19 essential OSM questions provide a framework for minimal OSM details requiring customisation to align with project requirements. Completion of OSM_KnowledgeBank (V1.0) templates is the responsibility of potential OSM stakeholders.
Step 3: evaluate and score your OSM capability and capacity
The completed set of templates provides the information about the available OSM capabilty and capacity needed for decision-making. The relative value of capacity and capability is calculated by the Project Team; each completed template is rated using a 1-5 scale. The calculation system is embedded in the OSM_KnowledgeBank. The score for each question is weighted in relation to the project requirements; this number is automatically added to the TOTAL POINTS template and totalled to a number between 475-0. The "points total" indicates capability and capacity available for procurement of an OSM project.
| Point Totals |  | OSM Procurement Model Readiness
ü | 300-475 | Project has significant OSM capability and capacity indicating likely success
| 150-299 | Project has minimum OSM capability and capacity indicating potential benefits from OSM procurement model
û | 0-149 | Project has inadequate OSM expertise or capacity indicating lack of OSM readiness
A full explanation off the evaluation method and the implications of the total points for OSM projct success is provided in the OSM Readiness Tool (V1.0) pdf available at Project 2.2, SBEnrc.com.au
OSM Capability and Capacity Templates
1 OSM Key Issues: Risk |  |  |  | Go to Risk questions
2 OSM Key Issues: Knowledge Management |  |  |  | Go to Knowledge Management questions
3 OSM Key Issues: Design |  |  |  | Go to Design questions
4 OSM Key Issues: Procurement |  |  |  | Go to Procurement questions
ADD SPECIFIC BUILDING PROJECT REQUIREMENTS TO TEMPLATE LISTS FOR BEST RESULTS

## RISK
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question R1: What are the risks involved when using an OSM method?
As with all construction methods, a project risk analysis is required. However, unfamiliarity with OSM means that special attention to the complexity of OSM procurement and supply options are required. The Project Manager is responsible for identifying specific risks associated with OSM adoption during the conceptual design stage. Each identified risk needs a well-defined risk reduction strategy as part of the project Risk Management Plan.
Examples of risk analysis factors | Identified OSM related risks |  |  | Risk reduction strategy
Financial complexity
Technical specifications
Procurement processes
Manufacturing processes
OSM integrated construction processes
Health & Safety in a variety of production locations
Community acceptance of OSM production processes
Other identified OSM related risks
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question R2: How does project cost for an OSM method compare with a conventional construction method cost?
It is often argued that the OSM method is a more expensive construction delivery method when compared with the conventional Design-Bid- Build method. This may be true if differences between direct and indirect costs are not taken into consideration during cost planning. The Project Manager is responsible for ensuring inclusion of both direct (on-site) and indirect (off-site) cost breakdown for all processes in the construction chain. Comparison of total project cost is necessary for a number of procurement methods to provide accurate 'value for money' estimates.
Examples of construction processes | Project cost of Conventional construction Design-Bid-Build method |  | Project cost of OSM construction (Design & Build) method |  | Project cost of OSM construction using other delivery method
Conceptual Design
Detail Design
Manufacturing
Pre-construction
Construction
Post-construction
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question R3: How does the project duration for an OSM method compare with a conventional construction method duration?
An industry perception that OSM components require long lead-times may prejudice the use of OSM. The Project Manager is responsible for ensuring inclusion of both direct (on-site) and indirect (off-site) duration breakdown for all processes in the construction chain. However, project duration also has direct and indirect duration factors. Comparison of total project duration is necessary for a number of procurement methods to provide accurate' value for money' estimates.
Examples of construction processes | Project duration of conventional construction Design-Bid-Build method |  | Project duration of OSM construction (Design & Build) method |  | Project duration of OSM construction using another delivery method
Conceptual Design
Detail Design
Manufacturing
Pre-construction
Construction
Post-construction
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | CL/PM |  |  |  | 0
Question R4: What is the range of the project manager's OSM experience?
For project teams with little OSM experience as a construction delivery method, OSM projects can be challenging and risky. A highly effective risk management strategy is to ensure that the Project Manager has significant OSM project experience. The responsibility of the Client and the Project Manager is to provide reassurance for the Project Team stakeholders that the project is managed from an OSM perspective.
Number of years OSM project experience________Number of OSM projects_______
Examples of building types | Company details | Scope of the OSM in project |  | Financial benefits of OSM in project |  | Non-financial benefits of OSM in project
Commercial
Residential
Government
Industrial
Educational
Transportation stations
Parking and storage
Military

## KNOWLEDGE MANAGEMENT
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question KM1: What is the range of the Architect's OSM experience?
For project teams with little experience of the construction delivery method, OSM projects can be challenging. A highly effective knowledge management strategy is to ensure that the Project Manager has significant OSM experience. The responsibility of the Project Manager is to identify stakeholders with OSM experience. Details of OSM experience related to building types provides an indication of the extent of OSM expertise. If OSM knowledge is exchanged before Detail Design finalisation, there are more opportunities to minimise waste and maximise effectiveness. Early involvement with suppliers, manufactures and builders with OSM experience will decrease the project risk.
Number of years OSM project experience________Number of OSM projects_______
Examples of building types | Company Details | Scope of the OSM in project |  | Financial benefits of OSM in project |  | Non-financial benefits of OSM in project
Commercial
Residential
Government
Industrial
Educational
Transportation stations
Parking and storage
Military
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question KM2: What is the range of the Design Engineer's OSM experience?
For project teams with little experience of the construction delivery method, OSM projects can be challenging. A highly effective knowledge management strategy is to ensure that the Project Manager has significant OSM experience. The responsibility of the Project Manager is to identify stakeholders with OSM experience. Details of OSM experience related to building types provides an indication of the extent of OSM expertise. If OSM knowledge is exchanged before Detail Design finalisation, there are more opportunities to minimise waste and maximise effectiveness. Early involvement with suppliers, manufactures and builders with OSM experience will decrease the project risk.
How many years of OSM experience?________How many OSM projects?_______
Examples of building types | Company Details | Scope of the OSM in project |  | Financial benefits of OSM in project |  | Non-financial benefits of OSM in project
Commercial
Residential
Government
Industrial
Educational
Transportation stations
Parking and storage
Military
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question KM3: What is the range of the Contractor's OSM experience?
For project teams with little experience of the construction delivery method, OSM projects can be challenging. A highly effective knowledge management strategy is to ensure that the Project Manager has significant OSM experience. The responsibility of the Project Manager is to identify stakeholders with OSM experience. Details of OSM experience related to building types provides an indication of the extent of OSM expertise. If OSM knowledge is exchanged before Detail Design finalisation, there are more opportunities to minimise waste and maximise effectiveness. Early involvement with suppliers, manufactures and builders with OSM experience will decrease the project risk.
How many years of OSM experience?________How many OSM projects?_______
Examples of building types | Company Details | Scope of the OSM in project |  | Financial benefits of OSM in project |  | Non-financial benefits of OSM in project
Commercial
Residential
Government
Industrial
Educational
Transportation stations
Parking and storage
Military
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question KM4: What is the project communication protocol?
OSM design processes require highly accurate information exchange between difference stakeholders in the Project Team via an integrated communication system. To ensure on-site and off-site connectivity an analysis of project stakeholder communication systems is necessary. A project communication protocol at the earliest stages of the building project is the necessary for knowledge sharing to support an OSM project delivery method. Effective and efficient knowledge transfer, in a number of specialist formats, is a principle requirement for OSM benefits to be measurable in a building project. The Project Manager is responsible for identifying all stakeholders and their software details.
Examples of stakeholders | Company details |  | Scope of responsibility |  | Communication software
Architect |  |  |  |  | e.g. Aconex
Structural Engineer
Transport Director
Environmental Manager
Mechanical Engineer
Electrical Engineer
Plumbing
Interior
Quantity Surveyor
Builder
Mechanical-Contractor
Quality Control Coordinator
Electrical-Contractor
Plumbing-Contractor
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM/M/S |  |  |  | 0
Question KM5: What OSM products' details are available before the Detail Design process begins?
An OSM delivery method requires accurate OSM product information, based on both supplier capability and capacity. It is important for architects and design engineers in the Project Team to have this information during their development of Detail Design. Because the requirements of OSM components are crucial for an accurate Detail Design, identification of the availability of the OSM components' details should be investigated before the Detail Design process begins. The Project Manager, OSM Manufacturers & Suppliers are responsible for providing the Detail Design team with accurate OSM capacity and capability information.
Example of building components | Products details |  | Complying standards |  | Are there CAD details available? |  | Are there BIM details available?
Substructure |  |  | e.g. AS/NZS 4600:2005 cold-formed steel structure
Superstructure |  |  | e.g. AS/NZS 4600:2005 steel structure
Concrete structure |  |  | e.g. AS/NZS 3600:2009 concrete
Smart monitoring system
Roof
Interior doors & frames
Mechanical system
Electrical system
Steel structure
Facade
Modular room unit
Fire fighting system

## DESIGN
Return to Front Page
Project:
Client: | [6 empty] | Data collection responsibility |  |  | Weight | Score | Points
[7 empty] | PM/AR/EC |  |  |  |  | 0
Question D1: What methods are used to adapt the Detail Design to include the available OSM components?
The conventional procurement method for building construction assumes a level of measurement accuracy that has a significant amount of adaptability. However OSM components are produced with the expectation of reducing waste of both human and material resources. This means more ridged adherence to uniform and highly accurate measurement. The design team needs to have the experience and skills to change calculation methodologies to accommodate the highly accurate and standardised OSM building components. Working with all stakeholders, the Project Manager, the Architect and the Consulting Engineer are responsible for analysing technical specifications of OSM components to ensure accurate calculations.
Examples of OSM components |  |  | What design methodology was changed? |  |  |  |  | What are the reasons for changing the design methodology?
Steel beams |  |  | from X method to Y method
Steel columns
Concrete floor
Duct work
Demountables
Modular shower and toilet cubicles
Other (if any)
Return to Front Page
Project:
Client: | [6 empty] | Data collection responsibility |  |  | Weight | Score | Points
[7 empty] | PM |  |  |  |  | 0
Question D2: What processes have been developed to ensure Detail Design coordination for OSM components?
In most conventional construction methods Detail Design is performed separately and construction coordination is the responsibility of the Construction Manager during the preparation of the shop drawings. Considerations of constructability are only considered through re-design of this late stage coordination which can be costly for the building project. Adopting an OSM method provides an opportunity to change how both the Detail Design and Shop Drawings are produced, by integrating OSM technical specifications with project requirements at an early stage. The best way to achieve this is to develop an OSM Integration Detail Design Coordination Protocol.
Examples of OSM components | Have transportation requirements and implications been considered for all phases? |  | Has coordination between stakeholders been considered during Conceptual Design? | Has coordination between stakeholders been considered during Detail Design? |  | Has coordination between stakeholders been considered during Manufacturing? |  | Has coordination between stakeholders been considered during Pre-construction? |  | What organisations are responsible for scoping OSM coordination?
Foundation work
Structural work
Facade work
Roof work
Interior work
Mechanical work
Electrical work
Other work (if any)
Return to Front Page
Project:
Client: | [6 empty] | Data collection responsibility |  |  | Weight | Score | Points
[7 empty] | AR/EC/MS |  |  |  |  | 0
Question D3: What design standards must be met by OSM components?
OSM component characteristics are different from traditional building components. As a result designers need to select design and calculation methods able to integrate the characteristics of the OSM components. The Project Team needs to identify OSM component impact on the building design and compliance issues to ensure design standards are integrated. A cooperative environment with all AEC stakeholders is necessary to take advantage of opportunities presented by an OSM procurement method. The Architect, Engineering Consultant, Manufacturers and Suppliers have the responsibility for collating OSM product standards details.
Examples of building components |  | System type |  |  | Required standard |  |  |  | Why was this standard selected?
Building structure |  | Structural design actions – General principles |  |  | AS/NZS 1170.0:2002
Steel structure |  | Steel reinforcing material |  |  | AS/NZS 4671:2001
Return to Front Page
Project:
Client: | [6 empty] | Data collection responsibility |  |  | Weight | Score | Points
[7 empty] | PM |  |  |  |  | 0
Question D4: Is “constructible” Building Information Modelling used in the project?
Building designers may have limited knowledge of the execution of construction OSM components. The IT systems used to generate technical drawings must be precise to ensure OSM manufacturing accuracy. The Project Manager is responsible for ensuring a Project Communication Protocol and the OSM Integration Detail Design Coordination Protocol that includes BIM capability and capacity within the project systems.
Examples of stakeholders |  | Company details |  |  | Software with OSM production compatibility |  |  |  | Scope of Responsibility
Architect
Structural engineer
Transport director
Environmental manager
Mechanical engineer
Electrical engineer
Plumbing
Interior
Quantity Surveyor
Builder
Mechanical contractor
Quality control coordinator
Electrical contractor
Plumbing contractor
Other stakeholders (if any)
Return to Front Page
Project:
Client: | [6 empty] | Data collection responsibility |  |  | Weight | Score | Points
[7 empty] | AR/EC/MS |  |  |  |  | 0
Question D5: What are the building tolerance standards?
During Detail Design of a building project, levels of tolerance are expected to meet industry and code standards. OSM products are also produced to tolerance standards, but to higher levels of tolerance accuracy. The Project Team members, Architect, Consulting Engineer, Manufacturers and Suppliers, should take responsibility during the design process for identifying the building tolerance standard of each OSM component.
Examples of OSM components |  | What tolerance standards have been used? |  |  |  | Is this tolerance standard included in the BIM?
Structural work |  | e.g. AS 2870 Residential slabs and footing
Facade work |  | e.g. AS 2047 Windows in building
Foundation work
Site preparation work
Roof work
Interior work
Mechanical work
Electrical work
Piping work
Overall work
Other works (if any)

## PROCUREMENT
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM |  |  |  | 0
Question P1: What are the construction site characteristics?
It is necessary to ensure the building site is OSM ready. The consideration of early Project Team stakeholder coordination for an OSM procurement method will provide specific production, transportation and installation details. An early analysis of compliance issues and special consideration authorisations required, will contribute to identifying both the direct and indirect costs. Identification of site characteristics will also provide details for coordinating manufacturing, transportation and the Project Communication Protocol.
1. Local infrastructure utilities such as water & electricity
2. Site accessibility for OSM transported components
3. Limitation posed to delivery of OSM components by the built environment
4. Site accessibility authorisation
5. Community issues related to OSM delivery and installation
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM/MS |  |  |  | 0
Question P2: Is OSM capacity available?
The vicious circle of not adopting an OSM procurement method means under-utilisation of capability, which leads to reduction in OSM production capacity. The Project Team needs to consider OSM capacity at an early stage because some OSM manufacturers have limited capacity, while other manufacturers maybe in an expansion phase. Availability of materials due to prior commitments also impacts on OSM manufacturer capacity. The Project Manager takes the lead in investigating OSM capacity.
Examples of OSM components | OSM Manufacturer details |  | OSM Manufacturer available materials |  | OSM Manufacturer capacity
Steel beams
Steel columns
Concrete floor
Duct work
Demountables
Modular shower and toilet cubicles
Other works (if any)
Project: | [8 empty] | Return to Front Page
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM/MS |  |  |  | 0
Question P3: Is OSM capability available?
Perceived absence of local OSM capability has been attributed to lack of stakeholder confidence in OSM procurement. Early analysis of available OSM capability will benefit all phases of a project ensuring of early matching of OSM component production with project specifications and project duration. The Project Manager is responsible for collecting information on OSM component capability from potential Manufacturers and Suppliers before commencing the design process.
Examples of OSM components | Available OSM skilled labour | Available OSM manufacturing facilities |  | Available OSM remote facilities |  | Available of OSM transportation
Steel Beams
Steel Columns
Concrete floor
Duct Work
Demountables
Modular shower and toilet cubicles
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | CM/B/MC/MS |  |  |  | 0
Question P4: What are the OSM components' quality control systems?
The concern with lack of quality for OSM components is often a mis-representation of the problem of ineffectual transfer of Detail Design. The problem is usually related to the lack of understanding the importance of detail accuracy of the design for the OSM components. All manufacturing processes have quality control systems in place, as do building projects. Project Team members sharing information about their quality control systems is another of the integrating processes required for an effective OSM procurement model.
Examples of OSM components | What quality control system is used in OSM manufacturing? | What quality control system is used in OSM transportation? |  | How is the OSM component quality control system incorporated with the construction site quality control system? |  | What organisations are responsible for scoping OSM quality control?
Foundation work
Structural work
Facade work
Roof work
Interior work
Mechanical work
Electrical work
Other works (if any)
Return to Front Page
Project:
Client: |  |  |  | Data collection responsibility |  | Weight | Score | Points
|  |  |  | PM/MS |  |  |  | 0
Question P5: How is on-site installation accuracy for OSM components achieved?
A perceived problem of OSM constancy is usually related to the lack of understanding the importance of measurement accuracy for the OSM components. OSM components are designed to a high level of specification accuracy possible in factory production necessary to ensure that every OSM component will fit during on-site installation. OSM component installation accuracy is assisted by site set-out tools and methodologies. The Project Manager leads the Project team in coordinating installation of OSM components by identifying the set-out methodologies, technologies and measurement accuracy necessary.
Example of OSM components | What are site set-out methodologies? |  | What technologies are used to ensure timely installation of OSM components? |  | What range of accuracy is expected?
Site preparation work
Foundation work
Structural work
Facade work
Roof work
Interior work
Mechanical work
Electrical work
Piping work
Overall work
Other works (if any)

## TOTAL POINTS
Project:
Client:
Question R1: What are the risks involved when using an OSM method? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question R2: How does project cost for an OSM method compare with a conventional construction method cost? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question R3: How does the project duration for an OSM method compare with a conventional construction method duration? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question R4: What is the range of the Project Manager's OSM experience? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question KM1: What is the range of the Architect's OSM experience? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question KM2: What is the range of the Design Engineer's OSM experience? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question KM3: What is the range of the Contractor's OSM experience? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question KM4: What is the project communication protocol? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question KM5: What OSM products' details are available before the Detail Design process begins? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question D1: What methods are used to adapt the Detail Design to include the available OSM components? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question D2: What processes have been developed to ensure Detail Design coordination for OSM components? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question D3: What design standards must be met by OSM components? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question D4: Is “constructible” Building Information Modelling used in the project? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question D5: What are the building tolerance standards? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question P1: What are the construction site characteristics? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question P2: Is OSM capacity available? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question P3: Is OSM capability available? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question P4: What are the OSM components' quality control systems? |  | Weight | Score | Points
|  | 0 | 0 | 0
Question P5: How is on-site installation accuracy for OSM components achieved? |  | Weight | Score | Points
|  | 0 | 0 | 0
| TOTAL POINTS | 0 | 0 | 0